## Slide 1: GAUTENG PROVINCE Combined Provincial Peer Review Teams' feedback on Peer Review Status Determination of February 2016
Birchwood Hotel Johannesburg 21st April 2016

## Slide 2: Comments on preparatory events/issues before peer review started on 1 February 2016
Issues | EKURHULENI | JOHANNESBURG | TSHWANE | SEDIBENG | WEST RAND
PROVINCE/DISTRICTS REVIEWED | NC-ZF Mgcawu and Prixley Kasemme |  | LP-Vhembe District health | LP-Vhembe District health | LP-Sekhukhune, Capricorn, Mopani Districts
September meeting | 1.The workshop was beneficial it helped to clarify a lot of issues and we learnt a lot from best practices. 2. Had tools given to the District 3.Benchmark from best performing Facility 4.Explanation and preparation of conducting reviews. 5. Meeting had the best outcomes 6. Allocation of facilities 7.Distribution of Draft version 15 manual 8.Some District presented the best practices .9. This was well organised and informative. |  |  |  | 
December meeting | 1. It really assisted especially with travelling arrangements and accommodation 2. Only one candidate was appointed or nominated to attend the meeting. 3. It was preparation for Peer Review, whereby we met one another with visitors for the District. 4.Meeting with MEC and arrangements were done. Limpopo versus Sedibeng District. 5. Provincial meeting held . 6. Teams were allocated 7. Tools were discussed some elements removed 8. This was well organised and informative but information reached us very late. |  |  |  | 
Software preparation | 1. The manual was user friendly 2. Two (2) team members were having capturing right 3. Only two(2) people were allowed to capture. 4. Passwords were provided without training. 5. Crash course was done at our District regarding soft ware i.e. capturing and the use of the system. 6. It was OK but too late sent to us and the on-line capturing of data was problematic as the network was unstable and this resulted in things having to be recaptured. |  |  |  | 
Communication to peer reviewers before it started (1 February | 1. Good 2. We managed to communicate with the nominated person in advanced 3. Communication was provided regarding accommodation, transport, contact person of the host district. 4. Material for use during reviews including Manuals, Checklist and Dashboard were provided 5. The duration of the Peer Reviews was communicated.6. The general communication was well done except the communication regarding the accommodation and travel arrangements. 7. The communication was not well in time and at the last minute causing some challenges |  |  |  | 
Any other comments on preparation | 1. The District managed to organize evaluation tools for the assessors 2. We were escorted to the relevant facilities 3. Facilities were supported by their District Managers. 4. Should be done in time and all the tools needed circulated well in advance to ensure that everybody to have it |  |  |  | 

## Slide 3: Comments on events / issues during the peer review from 31 January to 14 February 2016
Issues | EKURHULENI | JOHANNESBURG | TSHWANE | SEDIBENG | WEST RAND
PROVINCE/DISTRICTS REVIEWED | NC-ZF Mgcawu and Prixley Kasemme | EC | LP-Vhembe District health | LP-Vhembe District health | LP-Sekhukhune, Capricorn, Mopani Districts
Arrangement for travel to peer review district and return trip | POSITIVE COMMENTS |  |  |  | 
Shuttle service | POSITIVE COMMENTS |  |  |  | 
Flight tickets | POSITIVE COMMENTS |  |  |  | 
Car Hire | POSITIVE COMMENTS |  |  |  | 
Accommodation and meals | POSITIVE COMMENTS |  |  |  | 

## Slide 4: What went well and should be part of future peer reviews?
Issues | EKURHULENI | JOHANNESBURG | TSHWANE | SEDIBENG | WEST RAND
PROVINCE/DISTRICTS REVIEWED | NC-ZF Mgcawu and Prixley Kasemme |  | LP-Vhembe District health | LP-Vhembe District health | LP-Sekhukhune, Capricorn, Mopani Districts
 | Communication was good Plenary meeting was held Assessment tools (availability of assessment tools) Communication with visited District Teams got support from the host districts throughout the assessment period Continuous NDoH availability and support during capturing to clarify issues Good Lessons were learnt on certain processes |  |  |  | 

## Slide 5: What went wrong and should be improved on in future peer reviews
Issues | EKURHULENI | JOHANNESBURG | TSHWANE | SEDIBENG | WEST RAND
PROVINCE/DISTRICTS REVIEWED | NC-ZF Mgcawu and Prixley Kasemme |  | LP-Vhembe District health | LP-Vhembe District health | LP-Sekhukhune, Capricorn, Mopani Districts
 | Unavailability of cars Shortage of checklists and dashboards Different interpretations of tools. Rigidity and inflexibility during the assessment Guest assessors using background of National Core Standards Assessors not using option N/A this led to zero allocation Wrong capturing e.g. declaring generator not available but green for weekly checking Late arrival for assessment Assessors had difficulty in capturing Human Element Mistakes Having no stationery and modems Lack of Data capturers |  |  |  | 

## Slide 6: Thank You