## Slide 1: Provincial Peer Review Team Feedback
North West Province
KZN Peer Review
Experience Report
Date: 21/04/2016
Presented By: E.M. Mere

## Slide 2
Bojanala District | NMM District | Dr KK District | Dr RSM District
Amajuba | Zululand | Uthukele | Umkhanyakude
Harry Gwala | Uthungulu | Umzinyathi | 
Schedule of Pre-Reviews:
February 1, 2016 -February 10, 2016

## Slide 3: Preparatory Comments Before Peer Review
September meeting:
Some of the dash board elements were clarified
Relationship between ideal clinic and NCS
December meeting:
Clarity given on elements for common understanding
Created platform for district coordinators to meet with and interact with their peer reviewers,
Development of route plans,
Accommodation for peer review assessors was discussed,
Submission of the Identity documents of peer reviewers assessors for logistical purposes.

## Slide 4: Software Preparation
The software was prepared and availed,
Clarity was also provided on the software.

## Slide 5: Communication to Peer Reviewers
Correspondence well communicated in advance,
National held meetings with District coordinators.

## Slide 6: Comments on Preparation
Peer reviewers expected to be inducted on the new manual and checklist prior the assessment, which didn’t happen.

## Slide 7: Comments during Peer Review
Travelling Arrangements:
Shuttle services
  Excellent services to and from the airport,
Flight tickets
  Properly arranged and service provider promptly communicated through SMS’s,
Car hire
  Service was good except for Dr KK district, which received the cars two hours after arriving at the airport, they also had to buy fuel as their card was blocked, however, it was later resolved by NDOH.

## Slide 8: Comments during Peer Review cont…
Accommodation and meals:
Too far from the facilities e.g. Eshowe // Vryheid,
Poor reservation regarding some of our districts,
NMM team struggled with the meals throughout their stay at the venues, were even intimidated by being held hostage on their last day due to non confirmation of the booking for the entire stay.

## Slide 9: Comments during Peer Review cont…
Support by Host District:
Excellent & Fantastic support to all our districts,
Very good team spirit and positive attitude,
Support of Contact Person on Arrival:
Warm welcome on arrival at every sub- district and facility.

## Slide 10: Comments During Peer Review cont…
Support to Visit Facilities:
Accompanied by management (including District Managers, CEO, HR, Finance & SCM etc.) and partners at all times,
Support of Facility Managers:
Excellent support, warm welcome,
available and committed at all times.

## Slide 11: Availability Of Resources For Peer Review
Hardcopy of Peer Review Instruments:
Received very late, teams had already used their own,
Modems received very late, some not working at all, and for some teams the modems never arrived, and we had to use our own private modems.

## Slide 12: Availability of Resources for Peer Review
Ideal Clinic software (access, data upload and support):
The system was not open for capturing on the first day of the peer-review,
Support was provided throughout the assessment by NDOH.

## Slide 13: What Went Well and Should Be Part of Future Peer Review
Preparatory Phase:
Consultation with district representatives,
Criteria used for allocation of teams provided,
Availability of draft version prepared us.
During Peer Review:
Continuous support from NDOH teams,

## Slide 14: What went Wrong And Should Be Improved in Future Peer-Reviews
Preparatory Phase:
Criteria used to select the facilities was not objective and representative, e.g. In NMM only one facility in the entire district was assessed.
Unavailability of resources (modems) prior to assessments,
During Peer Review:
Inadequate logistical arrangements such as accommodation and meals for some team members.

## Slide 15: General Experience of Peer Reviews
Excellent experiential learning,
Good practices observed in and around KZN,
Resources are a key success factor in compliance,
Excellent positive staff attitudes observed in KZN.

## Slide 16: Additional Comments
Additional team members to cater for capturing, e.g. data capturers, team members,
Avoid frequent changing of the tool,
Induction of peer reviewers prior to the assessment on the review tool.

## Slide 17: CONCLUSION
Acknowledge and Appreciate this brilliant initiative by the NDoH.

## Slide 18: Thank you re a leboga